## User stories
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Owner | Yamini Bakshi-23706019
As a user, I want:
|  | No | User stories
|  | 1 | to create the snake game
SNAKE
|  | 2 | The snake to Eat prey
|  | 3 | The snake to move and change its direction
|  | 4 | The snake to grow by eating its prey
|  | 5 | The color of snake should be red and green
PREY
|  | 6 | User wants the color of the prey to be green
|  | 7 | The user wants the shape of prey to be round
|  | 8 | The user wants the position of prey to be random
GAMEBOARD
|  | 9 | The user can exit the window
|  | 10 | The user can resize the window
|  | 11 | The color of the gameboard is black
|  | 12 | The user will have an access to view the board

## Snake-game
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Developer | Yamini(23706019)
No | Level-1 tasks | Level-2 tasks | Level-3 tasks | Priority | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Note
1 | Create a repository for the project on GitHub |  |  | 1 | 100%
2 | Create and update product backlog |  |  | 1 | 100%
3 | Build the snake game as in the product backlog |  |  | 2
3.1 |  | Build the GUI
3.1.1 |  |  | GUI for gameboard |  | 100%
3.1.2 |  |  | GUI for login form |  | 100%
|  |  | GUI for player score |  | 100%
|  |  | GUI for Panels |  | 100%
|  |  | QUIT button |  | 100%
3.2 |  | Build the game logic
3.2.1 |  |  | Snake logic
3.2.1.1
3.2.1.2
3.2.1.3
3.2.2 |  |  | Prey Logic
3.2.2.1
3.2.3 |  |  | GameBoard Logic
3.2.3.1
3.2.3.2
3.2.3.3
4 | Test and deploy the game |  |  | 3 | 10%
4.1 | Logic Form |  |  |  | 100%
5 | Document the game |  |  | 4 | 0%